## Notes
Legend ✅ = KT indicates it’s deployed/working (my test is pending) ⚠️ = partially testable / config sensitive (common portal/B2C config issues) 🚧 = not ready / blocked (KT mentioned blocker) ❓ = not confirmed in KT (I must verify)

## Env_vs_Completed_Items
Story / Work item | What it is | Dev | DevInt | Test | Preprod | Prod | How to verify
8664 (Done) | Base Portal Registration + Sign-in + MFA + account mgmt | ✅ | ⚠️ | ✅ | ✅ | ✅ | Portal sign-in → MFA → land on dashboard
8790 (Done) | B2C ↔ Web API ↔ Dataverse auth wiring | ✅ | ⚠️ | ✅ | ✅ | ✅ | Trigger B2C flow and confirm API receives request (AppInsights)
8791 (Done) | Link B2C user ↔ Dynamics Contact | ✅ | ⚠️ | ✅ | ✅ | ✅ | Register → confirm mapping record exists / API log shows link success
8930 (Done) | Validate student info via API (ARN/DOB style) | ✅ | 🚧 | ✅ | ✅ | ✅ | Enter ARN/DOB (if policy wired) → see verify result + reason code/log
8797 (Done) | Branding (ASQA look & feel) | ✅ | ✅ | ✅ | ✅ | ✅ | Check hosted UI pages (logo/colors) during B2C screens
8798 (Done) | CI/CD for B2C policy deploy | ✅ | ✅ | ✅ | ✅ | ✅ | Run pipeline → see policy uploaded successfully
8800 (Done) | CI/CD for API deploy | ✅ | ✅ | ✅ | ✅ | ✅ | Run pipeline → App Service updated + health endpoint OK
9256 (Resolved) | Deploy to Test | — | — | ✅ | — | — | Confirm build version/last deployment time in Test
9413 (Resolved) | Deploy to Preprod | — | — | — | ✅ | — | Confirm build version/last deployment time in Preprod
9515 (Resolved) | Deploy to Prod | — | — | — | — | ✅ | Smoke test only: sign-in works
8942 (Resolved) | WAF for B2C | ⚠️ | ⚠️ | ✅ | ✅ | ✅ | WAF logs + ensure sign-in not blocked
8944 (Resolved) | DNS + WAF for Web API | ⚠️ | 🚧 | ✅ | ✅ | ✅ | API reachable from internet; gateway/WAF logs show requests
8946 (Resolved) | CAPTCHA for sign-up | ❓ | ❓ | ❓ | ❓ | ❓ | Try sign-up: do you see CAPTCHA? (KT suggests branch exists; main may not)
9433/9434/9455/9472/9274 (Resolved) | Portal UX fixes (mobile, errors, etc.) | ✅ | ✅ | ✅ | ✅ | ✅ | Open portal pages on mobile/desktop; check messages/layout

## Env_vs_RMA_Set1_Status
RMA Story ID (Set 1) | What it is | Dev | DevInt | Test | Preprod | Prod | Status per KT / what to check
RMA-01 | Invite email → ARN/DOB verify → signup → dashboard | 🚧 | 🚧 | 🚧 | 🚧 | 🚧 | KT indicates RMA is priority + not fully merged; needs your feature/rma-e2e work
RMA-02 | Invite-only enforcement (no bypass) | 🚧 | 🚧 | 🚧 | 🚧 | 🚧 | Not confirmed as complete; must implement + test bypass cases
RMA-03 | Role routing (RTO/CEO/II) | 🚧 | 🚧 | 🚧 | 🚧 | 🚧 | RTO policy is listed active (9628); not done
RMA-04 | Error codes + friendly pages (RMA-specific) | 🚧 | 🚧 | 🚧 | 🚧 | 🚧 | Not standardised yet; add reason codes + portal pages
RMA-05 | Dummy/Digital-ID mimic (demo now, plug real later) | 🚧 | 🚧 | 🚧 | 🚧 | 🚧 | Not started in main; you will build as part of RMA feature
RMA-06 | Merge RMA branch → main + regression pack | 🚧 | 🚧 | 🚧 | 🚧 | 🚧 | This is your delivery step after RMA stabilises

## Sheet9
Hi <Product Owner Name>, FYI current situation: even though B2C stories are marked Done/Resolved in the tracker, we don’t have a confirmed **end-to-end (E2E) sign-off baseline** across environments. In my testing, Dev/Test/Preprod are not behaving consistently, and I also don’t have the required contacts/access to fully validate Prod on my side. So to keep it safe and transparent, I propose we do the below plan **before we start any new stories**. **1) Business-led E2E Smoke Test (DevInt, Test, Preprod, Prod)** Can you please arrange testing in each environment using the attached/outlined “B2C E2E Smoke Test Pack” (Sign-in + MFA → dashboard, API journey, contact linking behaviour, ARN/DOB validation, branding, CAPTCHA, basic UX). For each env, we only need: * PASS/FAIL per test * Screenshot or short recording as evidence * Approx time tested + any error message text **2) Review + Confirm baseline scope** After you complete the smoke test results, you and I will have a short discussion to confirm: * What is working vs broken (per env) * What is “P0 baseline” that must be stable first (B2C/Portal/API/Dataverse wiring) **3) BA to create Stabilisation Backlog (with Acceptance Criteria)** Based on the test outcomes, we will route to BA to create a **Stabilisation Epic** with proper user stories + clear acceptance criteria (so nothing is “resolved but not verified”). This backlog will cover stabilisation only (no new features). **4) Fix + Re-test + Sign-off (all envs)** We will implement stabilisation fixes in a controlled order: DevInt → Test → Preprod → Prod, and we will attach evidence for each story. **5) BAU Pact (Definition of Done going forward)** We will agree a simple BAU pact: a story is “Done” only when: * deployed to target env * E2E tested using checklist * evidence attached (screenshots/logs) * PO/business sign-off recorded **6) Start new stories only after baseline is signed off** Once the baseline is stable and signed off in Prod + all lower environments, I will start picking up new stories confidently without risk of regression. If you’re ok, please let me know who will run the smoke test in each environment and when we can have a short review meeting after results are captured. Thanks, Praba
Hi <Product Owner Name>, I’d like to flag a risk and propose a controlled approach before we take on any new B2C work. **Current position** While several B2C items are marked as *Done/Resolved* in the tracker, we do not yet have a formally verified **end-to-end (E2E) baseline** across environments. In my checks, the Dev/Test/Preprod journeys are not consistently working end-to-end, and I also don’t currently have the required contacts/access to independently validate the full Prod journey. To ensure we proceed safely and with clear evidence, I recommend the following plan. --- ## Proposed plan (prior to commencing new stories) ### 1) Business/PO-led E2E smoke testing in all environments Please arrange a short E2E smoke test in **DevInt, Test, Preprod and Prod** using the “B2C E2E Smoke Test Pack” (I will provide/attach). This covers the baseline journeys such as: * Portal sign-in + MFA → land on dashboard * Portal → API journey (no user-facing errors) * B2C user ↔ CRM contact linking behaviour (journey consistency) * ARN/DOB validation (success/failure handling) * Branding, CAPTCHA and basic UX checks **Evidence required per environment (simple):** * Pass/Fail per test item * Screenshot or short recording * Approx. time tested + any on-screen error message --- ### 2) Joint review and confirmation of baseline scope Once results are captured, you and I will review outcomes and confirm: * What is working vs failing (by environment) * The agreed **P0 baseline** that must be stabilised first --- ### 3) BA to create a Stabilisation backlog with Acceptance Criteria Based on the test outcomes, we will route to BA to create a dedicated **B2C Stabilisation Epic**, with clear user stories and acceptance criteria (including “how to verify” and evidence expectations). This ensures we are not relying on “Resolved” status without verification. --- ### 4) Stabilise in a controlled sequence and obtain sign-off We will implement fixes and re-test in the standard promotion order: **DevInt → Test → Preprod → Prod** Each stabilisation item will include test evidence and PO/business sign-off before progressing. --- ### 5) BAU pact / Definition of Done (going forward) To prevent repeat of this issue, we align on a simple BAU pact: A story is “Done” only when it is: * Deployed to the required environment * E2E tested using the agreed checklist * Evidence attached (screenshots/log references) * PO/business sign-off recorded --- ### 6) Start new stories only after baseline is signed off Once the baseline is stable and signed off in **Prod and all lower environments**, I will commence new backlog items with confidence and lower regression risk. --- If you’re aligned with this approach, could you please confirm: 1. Who will run the smoke testing for each environment (DevInt/Test/Preprod/Prod) 2. A suitable time for a short review meeting once results are captured Thanks, Praba

## Env_vs_DigitalID_Set3_Status
Work item / Story | What it is | Dev | DevInt | Test | Preprod | Prod | Notes
9985 / 9987 / 10008 (Active) | 100-point ID (design/requirements/prototype) | 🚧 | 🚧 | 🚧 | 🚧 | 🚧 | KT: still discovery/POC stage, needs Set 3 feature plan

## Env_Blockers_And_Dependencies
Item | Dev | DevInt | Test | Preprod | Prod
INFRA-01 DevInt public DNS + gateway routing (B2C → API reachable) | n/a | 🚧 | n/a | n/a | n/a

## Sheet8
Workstream | Epic | What is changing | Who is impacted | Step-by-step user journey (screens) | What staff will do in CRM | What happens in background (simple flow) | Known errors + what user sees | Support steps | Test evidence + sign-off page | Owner | Target month
Platform & Environments | Env readiness (Dev/Test/DevInt/PreProd/Prod) | All environments will be clearly usable for testing with stable URLs, access, and connectivity so business can test without blockers. Providers/staff should not face random DNS/Gateway issues. | Business testers; Provider test users; RMA/QI/Intelligence staff; TechOps; Platform team | 1) Tester opens Portal URL 2) Tester runs health checks page 3) Tester runs login flow 4) Tester verifies CRM access and key pages | Provide environment map; confirm URLs; confirm test users exist; confirm CRM apps accessible; log and track environment issues | Portal/API/B2C URLs -> Gateway/WAF/DNS -> API -> Dataverse/CRM | DevInt DNS fail -> “Cannot reach service” API down -> friendly maintenance message | 1) Check env checklist 2) Confirm URL + DNS 3) Validate gateway rules 4) Check API health 5) Confirm Dataverse access 6) Raise platform ticket if needed | Evidence: Env checklist, URLs list, health check screenshots, access list. Sign-off: Platform + Business test lead | DEWR Platform + TechOps + Prabakaran
DevOps Automation | CI/CD for B2C + API + Portal | Release will become repeatable and safe: one-click deploy Dev→Test→PreProd with approvals, plus smoke tests and rollback steps, so business gets consistent releases. | Business owners; Testers; Dev team; DevOps/Platform; TechOps | No end-user screens. Release journey: 1) Approve release 2) Deploy to Test 3) Smoke tests 4) Deploy to PreProd 5) Sign-off 6) Prod deploy | Manage release gates; review release notes; approve PreProd/Prod; track deployment status | Repo -> Pipeline -> Deploy B2C policies + API + Portal -> Run smoke tests -> Publish report | Deploy failed -> release blocked with clear message Smoke fail -> “Stop promotion” | 1) Check pipeline logs 2) Fix config/secret 3) Re-run deploy 4) If Prod issue, run rollback playbook | Evidence: pipeline run links, release notes, smoke test report, rollback rehearsal proof. Sign-off: Platform + Business release approver | Prabakaran + DevOps/Platform
Uniform Framework | ASQA build standards uplift | All apps will follow one ASQA standard for CRM & Azure Devlopment, logging, errors, secrets, config and telemetry so support becomes easier and defects reduce. | All business areas using portal; Support; TechOps; Dev teams | Not a user journey. Business sees consistent error pages and consistent behaviour across apps. | Approve checklist; validate “friendly errors”; confirm runbooks exist; confirm logging available | Apps -> Standard libs/templates -> App Insights -> Support dashboards | Inconsistent errors removed -> users see friendly pages + reason codes across all apps | 1) Use reason code 2) Check runbook 3) Check dashboards 4) Escalate with correlation id | Evidence: signed checklist, standard error examples, telemetry dashboard, runbooks. Sign-off: TechOps + Business owner | Prabakaran + TechOps + Leads
RMA Onboarding | Invite-only onboarding end-to-end (B2C→API→Dataverse→Dashboard) | Public sign-up removed. Provider users can only access portal using invite link + ARN/DOB verification, then sign-in and land on correct dashboard with correct mapping. | Provider users (RTO/CEO/II); RMA staff; Support/TechOps; Security/Platform | 1) Email invite 2) Verify ARN+DOB screen 3) B2C sign-up/sign-in screen 4) Dashboard landing screen 5) Friendly error page if fail | Create/resend/expire invite; monitor invite status; check mapping; help user when failed; record reason codes | Email link -> Portal verify -> API validate -> B2C auth -> API link user/contact -> Dashboard | Invite expired -> “Link expired” (INV-EXPIRED) Wrong ARN/DOB -> “Not matching” (INV-NOMATCH) Used invite -> “Please sign in” (INV-USED) | 1) Ask reason code + time 2) Check invite record 3) Check contact mapping 4) Check logs 5) Resend/new invite or fix duplicate mapping | Evidence: happy path screenshots; negative path screenshots; CRM invite statuses; App Insights logs. Sign-off: Business + Security + TechOps | Prabakaran + Jamie support + DEWR platform for gateway
RMA Security | No-bypass hardening (replay/expired/duplicate) | We add protections so nobody can bypass invite checks or reuse links. Edge cases handled safely with audit trail and throttling if needed. | Provider users; Security; Support; Platform | Mostly same screens as onboarding. Extra outcomes: link reuse blocked; expired blocked; brute attempts blocked. | Support can see lockouts/flags; staff can issue new invites; security can review audit logs | Token/Invite rules -> API enforcement -> Logging/alerts | Replay attempt -> blocked + friendly message (INV-REPLAY) Too many attempts -> “Try later” (INV-LOCK) | 1) Confirm lock status 2) Validate audit logs 3) Create new invite 4) If abuse suspected, escalate to security | Evidence: security test cases, blocked attempts logs, throttling evidence. Sign-off: Security + Business owner | Prabakaran + Platform/Security
Digital Identity | Digital ID upgrade (myID/100-point) | We uplift identity proofing beyond ARN/DOB by integrating Digital ID (pilot first). If Digital ID fails, fallback manual verification exists. | Provider users; RMA staff; Security/Privacy; Support; DEWR/Services Australia | 1) Invite flow 2) Choose/trigger Digital ID step 3) Digital ID success -> continue 4) Fail -> fallback instructions | CRM stores identity status; staff can see verified/pending/failed; staff can trigger manual verification workflow | Portal -> B2C -> Digital ID provider -> API -> Dataverse identity status -> Dashboard | Digital ID unavailable -> “Try later or use manual path” Consent declined -> “Cannot proceed” | 1) Check identity status in CRM 2) Check logs 3) Provide manual verification steps 4) Re-initiate Digital ID attempt | Evidence: discovery pack, prototype demo, privacy+consent wording, pilot success criteria, PreProd evidence. Sign-off: Security/Privacy + Business | Prabakaran + Jamie + DEWR/Services Australia + Security/Platform
Documents & Records | Doc pipeline baseline (metadata/standards) | We define one clear rule for file metadata and records handling so documents always appear in correct SharePoint location and are audit-ready. | Portal users; Staff reviewers; Records team; TechOps | 1) Upload on portal 2) Confirmation screen 3) Staff opens CRM record 4) Staff opens SharePoint docs link | Confirm required metadata fields are present; verify SharePoint paths; raise gaps; approve standards | Portal upload -> Blob -> LogicApp -> SharePoint -> Metadata -> CastlePoint rules | Missing metadata -> staff sees “Document pending/needs fix” Copy failure -> logged and visible | 1) Check LogicApp run 2) Check SharePoint folder 3) Confirm metadata map 4) Trigger reprocess if supported | Evidence: standards sheet, baseline report, sample upload proof, records alignment sign-off | TechOps/Integration + Records + Honeybees
Documents & Records | Doc pipeline uplift + retry/reprocess | No silent failures. If file copy fails, it gets logged, alert raised, and can be reprocessed. Staff can trust evidence is not lost. | Portal users; Staff; Records; Support/TechOps | 1) Upload doc 2) Staff later sees doc in SharePoint with correct metadata 3) If failed: staff sees pending status (not missing) | Staff can see doc status; support can run retry; records team confirm compliance | Blob -> LogicApp -> SharePoint -> Reprocess queue -> Success/Fail dashboard | Copy fail -> “We received your upload; processing” (optional) Staff sees pending status; Ops alert triggers | 1) Identify submission/case id 2) Check failure dashboard 3) Run reprocess 4) Confirm metadata after success | Evidence: failure simulation + successful retry proof, dashboard screenshots, runbook. Sign-off: Records + Business + TechOps | TechOps/Integration + Honeybees
Tip-off Flow | Tip-off → triage → case → outcome hardening | Public can submit tip-offs reliably; staff triage converts to case consistently; evidence stored correctly; ops reporting exists for volumes and failures. | Public users; Intelligence staff; Records; TechOps | 1) Tip-off form screen 2) Upload evidence screen 3) Confirmation screen (no login) | Intelligence staff reviews submissions; converts to case; records outcome; accesses docs link | Portal -> Dataverse submission -> Docs pipeline -> Staff triage -> Case -> Outcome | Submission fail -> “Try later” Upload fail -> “Retry upload” Staff handoff missing -> flagged in reporting | 1) Confirm submission created 2) Check docs copy 3) Check triage workflow 4) Use reprocess and escalation | Evidence: end-to-end demo, triage to case proof, operational report screenshots, runbook approval. Sign-off: Intelligence business owner + Records + TechOps | Honeybees + TechOps
QI Journey | QI student response (cancel/not cancel) | Students can respond online clearly and safely, with consistent validation and recorded response, reducing manual follow-ups and confusion. | Students; QI staff; Support team | 1) Link open 2) Verify IRN/ARN + DOB screen 3) Cancel/Not Cancel selection screen 4) Confirmation screen | QI staff views response list; tracks status; triggers follow-up comms where needed | Portal -> Validation -> Dataverse response -> QI processing | Wrong details -> “Not matching” Link expired -> “Expired” System error -> friendly error page | 1) Check link validity 2) Confirm student record 3) Check response record created 4) Check logs for validation failure | Evidence: screenshots for both choices, CRM response evidence, negative tests. Sign-off: QI business owner | QI team + Honeybees
QI Import | QI bulk import uplift (no silent errors) | Bulk import will generate clear success/failure report with reasons, support retry and idempotent reruns so business trusts import outcomes. | QI staff; Data/ops; Support | Staff journey: 1) Upload file 2) Run import 3) Download report 4) Fix failed rows 5) Re-run safely | QI staff reviews import run record; sees counts; attaches report; confirms completion | Import engine -> Validate rows -> Write Dataverse -> Generate report -> Monitoring alerts | Missing fields -> listed in report Duplicate -> listed in report Invalid DOB -> listed in report | 1) Use report to identify failures 2) Fix source file 3) Re-run failed rows only 4) Monitor results | Evidence: import report samples, scale test results, monitoring alerts, runbook. Sign-off: QI + TechOps | QI team + Honeybees + TechOps
PARMI Model | PARMI minimum provider model locked | We agree one canonical model for provider master data (ABN/status/address/location/scope) so portal updates and publishing work consistently. | RMA business; PARMI team; Portal team; Publishing/reporting teams | Not an end-user screen. Output is agreed definitions and validation rules. | Staff uses rules in approvals; staff understands terms (address vs delivery location etc.) | Business rules -> Dataverse/PARMI schema -> Validations -> Integration mapping | Inconsistent data prevented: validation messages shown during approvals/updates | 1) Refer model spec 2) Raise change request if new field needed 3) Follow data governance process | Evidence: model spec, mapping rules, sign-off notes. Sign-off: PARMI lead + Business owner | PARMI team (you+Pradeep)
Provider Updates | Wave 1 provider updates (basic details) | Providers can submit basic changes in new portal; staff approves; PARMI updated; audit trail kept. | Providers; RMA staff; PARMI team | 1) Login 2) Update details screen 3) Submit screen 4) Confirmation screen 5) Status tracking screen | Review submission queue; approve/reject; view audit; confirm PARMI updated | Portal -> Submission -> CRM approval -> PARMI update -> Status back to portal | Validation fail -> inline message Rejected -> reason shown PARMI update fail -> staff sees failure status | 1) Check submission id 2) Check approval decision 3) Check PARMI update log 4) Retry/resolve failure | Evidence: end-to-end PreProd proof, rejection example, audit trail proof. Sign-off: Business owner + PARMI | PARMI team + Honeybees
Provider Updates | Wave 2 provider updates (delivery locations + complex) | Providers can manage delivery locations and complex updates with strong validations; staff approvals and audit ensure safe updates. | Providers; RMA staff; PARMI team; Publishing team | 1) Login 2) Manage locations/scope mapping screens 3) Validation warnings screen 4) Submit + confirmation | Approve complex submissions; check validations; audit changes; confirm PARMI update and publish readiness | Portal -> Complex submission -> CRM approval -> PARMI update -> Publish triggers later | Scope/location mismatch -> validation warning Data conflict -> staff sees “Needs review” Integration fail -> retry path | 1) Use validation guidance 2) Staff review checklist 3) If fail, retry or escalate integration support | Evidence: complex scenario tests, validation proof, audit trail proof. Sign-off: Business + PARMI + TechOps | PARMI team + Honeybees
Publishing Strategy | PARMI ↔ TGA publish strategy locked | We confirm how publishing will transition away from ASQAnet dependency and set reconciliation rules so business can trust what is published and when. | Business owners; PARMI team; Integration team; Reporting | Not a portal screen. Business deliverable is strategy and operational reporting view. | Staff can check publish status and raise issues using reason codes/IDs | RMA approved change -> PARMI update -> Middleware publish -> Log status -> Reconcile report | Publish deferred/failed -> visible status (not silent) Validation fail -> clear reason in log | 1) Check publish status 2) Retry failed publish 3) Run reconciliation report 4) Escalate to integration if repeated failures | Evidence: strategy doc, reconciliation design, sign-off. | PARMI team + Platform/Integration
Middleware Publishing | Publish middleware build (audit + retry + reconciliation) | We build a publish layer that logs every publish attempt, supports retry, and produces reconciliation report (PARMI vs TGA). | PARMI team; Integration team; Support; Business owners | Business journey: 1) Change approved 2) Publish status shows Succeeded/Failed 3) Failure can be retried 4) Reconciliation report available | Staff/support can view status dashboard, re-trigger publish via support process | PARMI -> Middleware -> TGA -> Publish log -> Retry queue -> Reconciliation report | TGA down -> failed + scheduled retry Auth fail -> immediate failure Data invalid -> reject with clear message | 1) Locate correlation id 2) Check logs 3) Retry 4) Confirm success 5) Update business if delay | Evidence: pilot publish run, failure+retry proof, dashboards, runbook. Sign-off: Business + TechOps | PARMI team + Integration engineers
Finance | Business Central invoice/payment integration | Portal/CRM will request invoices from Business Central and show invoice/payment status clearly with reconciliation rules, reducing mismatches and manual chasing. | Providers paying; Finance team; RMA staff; BC vendor | 1) Provider submits request 2) Invoice generated 3) Provider pays 4) Status updates shown in CRM/portal | Staff sees invoice status; handles exceptions; finance runs reconciliation checks | Portal/CRM -> BC invoice create -> Payment -> Status sync back -> Reconciliation checks | BC unavailable -> “Invoice delayed” Payment mismatch -> “Pending reconciliation” Sync fail -> retry path | 1) Check invoice id in BC 2) Check sync logs 3) Apply reconciliation process 4) Escalate vendor if needed | Evidence: PreProd invoice+payment test, reconciliation proof, runbook. Sign-off: Finance + Business | Tech Infosys + Finance SMEs + Honeybees
Data Quality & Fraud | PARMI data quality rules + fraud cross-checks | We improve trust in published/provider data with automated checks, discrepancy reporting, and fraud indicators (scope/location mismatch patterns) for better triage. | PARMI team; Intelligence; RMA business; Reporting | Not always a portal screen. Outputs are dashboards and discrepancy reports for staff use. | Staff views discrepancy report; triage uses indicators; outcomes tracked in reporting | PARMI data -> Quality rules -> Discrepancy report -> Fraud indicators -> Reporting dashboard | Discrepancy found -> appears in report Fraud indicator -> flag for triage review | 1) Review report 2) Fix data via approved process 3) Re-run checks 4) Use triage guidance for flagged items | Evidence: rules doc, automated check results, dashboards. Sign-off: Business owners | PARMI team + Honeybees
Cutover & Decommission | ASQAnet transition plan (read-only, migration, rollback) | We plan and execute safe cutover steps so more functions move to new portal/PARMI and legacy ASQAnet becomes read-only/disabled in controlled way with rollback. | All staff; Providers; Support; Platform; Business owners | Business journey: 1) Comms sent 2) Users use new portal 3) Legacy features switched to read-only 4) Monitoring confirms stability | Staff follow cutover checklist; manage comms; support escalations; confirm rollback readiness | New portal live -> Monitoring -> Legacy restrictions -> Reconciliation checks -> Hypercare support | Confusion -> FAQs Access issues -> support runbook Cutover issue -> rollback plan activated | 1) Use cutover runbook 2) Daily monitoring 3) Rapid triage 4) Rollback if required | Evidence: cutover playbook, comms pack, rollback test proof, hypercare plan. Sign-off: Business + TechOps + Platform | PARMI team + Platform + Business

## Roadmap (2)
Epic/Feature | Real-world business flow | Portal name used | ARMS Application (asqa staff app) | Other systems involved | Output / Result | Q1 deliverables (Jan–Mar) | Q2 deliverables (Apr–Jun) | Q3 deliverables (Jul–Sep) | Q4 deliverables (Oct–Dec) | Owner | Definition of Done
1 | RMA Invite-only onboarding end-to-end (B2C → API → Dataverse → Dashboard) Provider user gets invite, verifies ARN/DOB, signs up, lands on right dashboard; no public sign-up allowed | ASQA Portal (Next Gen) (RMA portal pages) | RMA CRM App (staff manage invitations, submissions, routing) | Azure AD B2C, Web API, Dataverse, App Insights, WAF, DNS/Gateway | Secure invite-only portal access working end-to-end; correct user-contact mapping; supportable errors | 1)Stabilise invite flow in Dev/Test (invite email → ARN/DOB verify → signup). 2)Implement no-bypass enforcement. 3)Add reason codes + friendly error pages. 4)Fix DevInt DNS/gateway so B2C→API reachable in DevInt. 5)Complete role routing (RTO/CEO/II) + verify across Test/PreProd. 6)Confirm CAPTCHA requirement and implement if missing. 7)Add regression pack (happy + negative paths). 8)Hardening: edge cases (duplicate contact, wrong ARN/DOB, expired invite, replay attack). 9)Improve monitoring + alerts for auth failures and API issues. 10)Merge RMA work to main branch + execute full regression + production smoke. 11)BAU handover pack ready. |  |  |  | Prabakaran (RMA/B2C dev) + Jamie for priority/support; DEWR for gateway/WAF | 1) No public signup (invite required). 2) ARN/DOB validation enforced + Logging + Runbook. 3) Contact link created correctly. 4) Role routing works. 5) Friendly error messages and pages + reason codes. 6) Dev/Test/PreProd/Prod smoke tests passed + monitoring alerts configured.
2 | Digital ID upgrade (100-point ID / myID) – workshop → encage dewr and service australia → design → prototype → plug into invite flow Stronger identity proofing for provider users (beyond ARN/DOB) | ASQA Portal (Next Gen) | RMA app (invitation + identity status) | Digital ID provider (myID/100-point), B2C custom policies, Web API, Dataverse, monitoring | Verified high-trust identity for portal access; future-ready compliance | 1)Discovery: confirm requirement scope, user journeys, data fields, consent, error handling. Define integration approach (B2C policy + API). Build dummy/mimic in portal for demo path (as per KT). | 1)Prototype integration in Dev/Test with limited scope. Define fallback (manual verification) + support model. 2)Hardening: security review, penetration-style negative tests, performance, monitoring, privacy. 3)Production-ready go-live plan + phased rollout (pilot group first) + BAU handover. |  |  | Prabakaran + Jamie/Business + (DEWR, Services Australia)Security/Identity team + Platform | 1) Identity journey approved by business/security. 2) End-to-end integration works in PreProd. 3) Logs + audit + support model defined. 4) Pilot success criteria met. 5) Rollout plan for prod agreed.
3 | Tip-off → triage → case → outcome | ASQA Portal (Tip-off) | Intelligence app (Submission → UCM Case) | Blob → Logic App → SharePoint, CastlePoint | Decision/action taken | Hardening: performance/usability + support runbook for tip-off flow. | Improve automation handoff (submission → case) consistency. | Operational reporting: volume, turnaround, doc failures. | Release readiness: stable flow, support model for peak periods. | Honeybees + TechOps for ops readiness | DoD: End-to-end works in PreProd with test evidence; monitoring + runbook approved; zero known P1 defects open for go-live.
4 | QI: impacted students respond → cancel/not cancel | ASQA Portal (IRN/ARN + DOB) | QI app | Vision6, ADF (current), Blob→Logic App→SharePoint | Students assessed, qualification cancelled/upheld | Review current import gaps (perf, silent errors like DOB). Align QI sign-up with universal invitation model direction. | Implement uplift plan (start productionising Danuka improvements) + add import error report. | Scale testing: larger imports + idempotent re-run + monitoring. | Prod readiness: stable import + clear support process; consistent portal onboarding UX. | QI team + Honeybees (app/portal) + Palmy team (invitation standard alignment) | DoD: Import runs with success/failure report, retries supported, no silent failures; portal onboarding verified; business sign-off in PreProd.
5 | Document + records handling | ASQA Portal uploads | Intelligence / QI / RMA apps | Blob, Logic App, SharePoint, CastlePoint, replacing Objective/EDRMS | Evidence stored with audit + retention | Baseline review: metadata standards + known failures + gaps. | Implement uplift (Danuka file copy improvements) in Dev/PreProd. | Monitoring + retry/reprocess mechanism; consistency across apps. | Prod-grade doc pipeline: stable + auditable + CastlePoint alignment; reduced manual fixes. | TechOps/Integration (file pipeline) + Honeybees (app metadata usage) + Records/CastlePoint stakeholders | DoD: Files always land in SharePoint with correct metadata; failures logged + reprocessable; records rules satisfied; business accepts in PreProd.
6 | Application uplift (CRM + Azure apps) to follow ASQA uniform framework from dev → prod Standardise development patterns, logging, error handling, security, config, solution packaging | ASQA Portal (Next Gen) + internal admin portals (where applicable) | RMA / Intelligence / QI apps (and future apps) | Dataverse solutions, Azure Functions/APIs, Key Vault, App Insights, SharePoint, integration components | Consistent ASQA way-of-working: easier support, less defects, faster releases |  |  | 1)Define ASQA “uniform framework checklist” (logging, config, secrets, errors, telemetry, naming). Identify gaps in current CRM/Azure components. 2)Uplift highest-risk components first (auth endpoints, invitation validation, contact link, error handling). Standardise common libs/templates. 3)Expand uplift across remaining components + enforce via PR checks (linting, security scans, config rules). 4)Full compliance baseline achieved for all in-scope apps; BAU support docs + architecture updated. |  | Prabakaran (solution architect/dev) + TechOps + leads | 1) Framework checklist signed-off. 2) All apps meet baseline (logging, config, error standard). 3) Secrets in Key Vault. 4) Telemetry consistent. 5) Support runbooks available.
7 | Full DevOps automation (CI/CD + release governance) for B2C + API + Portal | N/A (deployment automation) | RMA / Intelligence / QI apps (and future apps) | Azure DevOps pipelines, B2C policy deploy, App Service deploy, Key Vault, App Insights, WAF/Gateway configs | One-click reliable release to Test/PreProd/Prod with approvals, tagging, rollback | Review existing pipelines (B2C + API) and add standard promotion flow (gates/approvals). Add version stamping + automated smoke test step. |  |  | 1)Automate environment configuration drift checks (WAF/DNS/gateway rules). Add release notes generation + artifact retention policy. 2)Add “regression pack execution” automation hooks (at least triggerable). Improve alerts + dashboards for auth/API failures. 3)Production support automation: scheduled health checks, alert runbooks, “hotfix path” defined and tested. | Prabakaran + DevOps/Platform | 1) Pipeline deploys B2C policies + API consistently. 2) Approval gates for PreProd/Prod. 3) Automated smoke tests. 4) Rollback documented and rehearsed. 5) Monitoring dashboards and alerts live.
8 | Organisation applies to become registered / updates registration | ASQAnet (today), ASQA Portal (target) | RMA app | Palmy, TGA | Provider registered/updated, public register updated | Palmy minimum model locked (ABN, statuses, address/location). Standard invitation/sign-up approach agreed for providers. | RMA Portal Wave 1 in PreProd (basic updates like contacts) + submission auto/quick-review flow. | RMA Portal Wave 2 (delivery locations + complex updates) + validations + audit trail. | Cutover-ready: majority common provider updates available; first safe decommission steps planned/executed. | Palmy team (you + Pradeep) for model/integration + Honeybees for portal/RMA build | PreProd DoD (Q2/Q3): End-to-end tested (portal → submission → Palmy update). Prod DoD (Q4): Feature live + support runbook + rollback. Decom DoD: ASQAnet function disabled/read-only + users migrated + monitoring stable.
9 | Normal training + student gets certificate (good path) | No ASQA portal usually | No ARMS app usually | TGA, Palmy | Student receives valid qualification | Define “clean data” rules in Palmy so public verification is accurate. | Ensure RMA updates maintain scope/locations correctly in Palmy. | Add reconciliation checks (changes vs published). | Reporting confidence: business trust in published provider/scope/location info. | Palmy team | DoD: Data quality rules documented + automated checks in place + discrepancies report available.
10 | Fraud happens (RPL misuse / fake evidence / outside scope) | Often via ASQA Portal Tip-off | Intelligence app | TGA/Palmy, SharePoint | Fraud identified, leads to investigation | Review tip-off intake data points for better triage + evidence needs. | Improve triage guidance + consistent outcomes (close/refer/case). | Add cross-check capability using Palmy/TGA data (scope/location mismatch indicators). | Dashboards/reporting for fraud patterns and outcomes. | Honeybees (Intelligence + portal); Palmy team supports cross-check data | DoD: Triage outcomes consistent + cross-checks working + operational reporting visible in PreProd and accepted by business.
11 | Data Sync & Publishing (Palmy ↔ TGA / transition from ASQAnet) Keep provider master data consistent while moving from ASQAnet as publisher to ARMS/Palmy as source of truth | ASQAnet Portal (today) + ASQA Portal (Next Gen) | Mainly RMA app (changes originate) + any apps that reference provider data | Palmy (curated dataset), TGA (training.gov.au), ASQAnet, Modern Data Warehouse (reporting), Middleware layer (integration APIs/queues) | A controlled, traceable, reconcilable way to publish provider data to TGA without double-handling | Publish strategy locked: decide transition pattern (short-term push-back to ASQAnet vs direct publish from Palmy). Canonical model decisions: ABN/address/status rules. Define reconciliation needs: what we must log per publish. | Build publish “middleware shape” in PreProd: publish request/response logging, correlation IDs, retry model draft. Start syncing RMA-approved changes into Palmy consistently. | Pilot publishing pipeline: end-to-end run for selected data types (e.g., contacts + locations) in PreProd. Add reconciliation dashboard/report: what changed, what published, what failed. | Production-ready publish layer: stable retries + monitoring. Reduce ASQAnet dependency: flip direction so only residual legacy feeds ARMS/Palmy. Prepare cutover playbook. | Palmy team (you + Pradeep) lead; Honeybees support (RMA change triggers); platform/integration engineers as needed | DoD: 1) Every publish has audit log + status (Sent/Succeeded/Failed). 2) Failures are reprocessable (no silent loss). 3) Reconciliation report exists (Palmy vs TGA publish status). 4) Business sign-off in PreProd + runbook for support.
12 | Finance: invoices/payments linked to applications | ASQAnet today, ASQA Portal future | Mostly RMA app + finance visibility | Business Central, XML today, vendor Tech Infosys | Payment matched, finance reconciled | Document current mismatch issues; confirm target architecture (BC as source of truth). | Design “portal requests invoice from BC” approach + required data fields/status in RMA. | Build/POC integration + reconciliation approach; define rollout plan. | Start phased rollout for BC-first invoicing for new portal functions (or ready-to-implement). | Tech Infosys (BC vendor) + Honeybees + Jamie/Finance SMEs | DoD: Finance process reconciles (agreed checks), invoice/payment statuses visible, runbook and audit trail documented, PreProd tested with sample payments.

## Roadmap
Epic/Feature | Real-world business flow | Portal name used | ARMS Application (staff app) | Other systems involved | Output / Result | Q1 deliverables (Jan–Mar) | Q2 deliverables (Apr–Jun) | Q3 deliverables (Jul–Sep) | Q4 deliverables (Oct–Dec) | Owner | Definition of Done
1 | Organisation applies to become registered / updates registration | ASQAnet (today), ASQA Portal (target) | RMA app | Palmy, TGA | Provider registered/updated, public register updated | Palmy minimum model locked (ABN, statuses, address/location). Standard invitation/sign-up approach agreed for providers. | RMA Portal Wave 1 in PreProd (basic updates like contacts) + submission auto/quick-review flow. | RMA Portal Wave 2 (delivery locations + complex updates) + validations + audit trail. | Cutover-ready: majority common provider updates available; first safe decommission steps planned/executed. | Palmy team (you + Pradeep) for model/integration + Honeybees for portal/RMA build | PreProd DoD (Q2/Q3): End-to-end tested (portal → submission → Palmy update). Prod DoD (Q4): Feature live + support runbook + rollback. Decom DoD: ASQAnet function disabled/read-only + users migrated + monitoring stable.
2 | Normal training + student gets certificate (good path) | No ASQA portal usually | No ARMS app usually | TGA, Palmy | Student receives valid qualification | Define “clean data” rules in Palmy so public verification is accurate. | Ensure RMA updates maintain scope/locations correctly in Palmy. | Add reconciliation checks (changes vs published). | Reporting confidence: business trust in published provider/scope/location info. | Palmy team | DoD: Data quality rules documented + automated checks in place + discrepancies report available.
3 | Fraud happens (RPL misuse / fake evidence / outside scope) | Often via ASQA Portal Tip-off | Intelligence app | TGA/Palmy, SharePoint | Fraud identified, leads to investigation | Review tip-off intake data points for better triage + evidence needs. | Improve triage guidance + consistent outcomes (close/refer/case). | Add cross-check capability using Palmy/TGA data (scope/location mismatch indicators). | Dashboards/reporting for fraud patterns and outcomes. | Honeybees (Intelligence + portal); Palmy team supports cross-check data | DoD: Triage outcomes consistent + cross-checks working + operational reporting visible in PreProd and accepted by business.
4 | Tip-off → triage → case → outcome | ASQA Portal (Tip-off) | Intelligence app (Submission → UCM Case) | Blob → Logic App → SharePoint, CastlePoint | Decision/action taken | Hardening: performance/usability + support runbook for tip-off flow. | Improve automation handoff (submission → case) consistency. | Operational reporting: volume, turnaround, doc failures. | Release readiness: stable flow, support model for peak periods. | Honeybees + TechOps for ops readiness | DoD: End-to-end works in PreProd with test evidence; monitoring + runbook approved; zero known P1 defects open for go-live.
5 | QI: impacted students respond → cancel/not cancel | ASQA Portal (IRN/ARN + DOB) | QI app | Vision6, ADF (current), Blob→Logic App→SharePoint | Students assessed, qualification cancelled/upheld | Review current import gaps (perf, silent errors like DOB). Align QI sign-up with universal invitation model direction. | Implement uplift plan (start productionising Danuka improvements) + add import error report. | Scale testing: larger imports + idempotent re-run + monitoring. | Prod readiness: stable import + clear support process; consistent portal onboarding UX. | QI team + Honeybees (app/portal) + Palmy team (invitation standard alignment) | DoD: Import runs with success/failure report, retries supported, no silent failures; portal onboarding verified; business sign-off in PreProd.
6 | Finance: invoices/payments linked to applications | ASQAnet today, ASQA Portal future | Mostly RMA app + finance visibility | Business Central, XML today, vendor Tech Infosys | Payment matched, finance reconciled | Document current mismatch issues; confirm target architecture (BC as source of truth). | Design “portal requests invoice from BC” approach + required data fields/status in RMA. | Build/POC integration + reconciliation approach; define rollout plan. | Start phased rollout for BC-first invoicing for new portal functions (or ready-to-implement). | Tech Infosys (BC vendor) + Honeybees + Jamie/Finance SMEs | DoD: Finance process reconciles (agreed checks), invoice/payment statuses visible, runbook and audit trail documented, PreProd tested with sample payments.
7 | Document + records handling | ASQA Portal uploads | Intelligence / QI / RMA apps | Blob, Logic App, SharePoint, CastlePoint, replacing Objective/EDRMS | Evidence stored with audit + retention | Baseline review: metadata standards + known failures + gaps. | Implement uplift (Danuka file copy improvements) in Dev/PreProd. | Monitoring + retry/reprocess mechanism; consistency across apps. | Prod-grade doc pipeline: stable + auditable + CastlePoint alignment; reduced manual fixes. | TechOps/Integration (file pipeline) + Honeybees (app metadata usage) + Records/CastlePoint stakeholders | DoD: Files always land in SharePoint with correct metadata; failures logged + reprocessable; records rules satisfied; business accepts in PreProd.
8 | Data Sync & Publishing (Palmy ↔ TGA / transition from ASQAnet) Keep provider master data consistent while moving from ASQAnet as publisher to ARMS/Palmy as source of truth | ASQAnet Portal (today) + ASQA Portal (Next Gen) | Mainly RMA app (changes originate) + any apps that reference provider data | Palmy (curated dataset), TGA (training.gov.au), ASQAnet, Modern Data Warehouse (reporting), Middleware layer (integration APIs/queues) | A controlled, traceable, reconcilable way to publish provider data to TGA without double-handling | Publish strategy locked: decide transition pattern (short-term push-back to ASQAnet vs direct publish from Palmy). Canonical model decisions: ABN/address/status rules. Define reconciliation needs: what we must log per publish. | Build publish “middleware shape” in PreProd: publish request/response logging, correlation IDs, retry model draft. Start syncing RMA-approved changes into Palmy consistently. | Pilot publishing pipeline: end-to-end run for selected data types (e.g., contacts + locations) in PreProd. Add reconciliation dashboard/report: what changed, what published, what failed. | Production-ready publish layer: stable retries + monitoring. Reduce ASQAnet dependency: flip direction so only residual legacy feeds ARMS/Palmy. Prepare cutover playbook. | Palmy team (you + Pradeep) lead; Honeybees support (RMA change triggers); platform/integration engineers as needed | DoD: 1) Every publish has audit log + status (Sent/Succeeded/Failed). 2) Failures are reprocessable (no silent loss). 3) Reconciliation report exists (Palmy vs TGA publish status). 4) Business sign-off in PreProd + runbook for support.
9 | RMA Invite-only onboarding end-to-end (B2C → API → Dataverse → Dashboard) Provider user gets invite, verifies ARN/DOB, signs up, lands on right dashboard; no public sign-up allowed | ASQA Portal (Next Gen) (RMA portal pages) | RMA app (staff manage invitations, submissions, routing) | Azure AD B2C, Web API, Dataverse, App Insights, WAF, DNS/Gateway | Secure invite-only portal access working end-to-end; correct user-contact mapping; supportable errors | Stabilise invite flow in Dev/Test (invite email → ARN/DOB verify → signup). Implement no-bypass enforcement. Add reason codes + friendly error pages. Fix DevInt DNS/gateway so B2C→API reachable in DevInt. | Complete role routing (RTO/CEO/II) + verify across Test/PreProd. Confirm CAPTCHA requirement and implement if missing. Add regression pack (happy + negative paths). | Hardening: edge cases (duplicate contact, wrong ARN/DOB, expired invite, replay attack). Improve monitoring + alerts for auth failures and API issues. | Merge RMA work to main + execute full regression + production smoke. BAU handover pack ready. | You (RMA/B2C dev) + Jamie for priority/support; TechOps for gateway/WAF | DoD: 1) No public signup (invite required). 2) ARN/DOB validation enforced + logged. 3) Contact link created correctly. 4) Role routing works. 5) Friendly error pages + reason codes. 6) Dev/Test/PreProd/Prod smoke tests passed + monitoring alerts configured.
10 | Full DevOps automation (CI/CD + release governance) for B2C + API + Portal | N/A (deployment automation) | N/A | Azure DevOps pipelines, B2C policy deploy, App Service deploy, Key Vault, App Insights, WAF/Gateway configs | One-click reliable release to Test/PreProd/Prod with approvals, tagging, rollback | Review existing pipelines (B2C + API) and add standard promotion flow (gates/approvals). Add version stamping + automated smoke test step. | Automate environment configuration drift checks (WAF/DNS/gateway rules). Add release notes generation + artifact retention policy. | Add “regression pack execution” automation hooks (at least triggerable). Improve alerts + dashboards for auth/API failures. | Production support automation: scheduled health checks, alert runbooks, “hotfix path” defined and tested. | You + DevOps/Platform | DoD: 1) Pipeline deploys B2C policies + API consistently. 2) Approval gates for PreProd/Prod. 3) Automated smoke tests. 4) Rollback documented and rehearsed. 5) Monitoring dashboards and alerts live.
11 | Application uplift (CRM + Azure apps) to follow ASQA uniform framework from dev → prod Standardise development patterns, logging, error handling, security, config, solution packaging | ASQA Portal (Next Gen) + internal admin portals (where applicable) | RMA / Intelligence / QI apps (and future apps) | Dataverse solutions, Azure Functions/APIs, Key Vault, App Insights, SharePoint, integration components | Consistent ASQA way-of-working: easier support, less defects, faster releases | Define ASQA “uniform framework checklist” (logging, config, secrets, errors, telemetry, naming). Identify gaps in current CRM/Azure components. | Uplift highest-risk components first (auth endpoints, invitation validation, contact link, error handling). Standardise common libs/templates. | Expand uplift across remaining components + enforce via PR checks (linting, security scans, config rules). | Full compliance baseline achieved for all in-scope apps; BAU support docs + architecture updated. | You (solution architect/dev) + TechOps + leads | DoD: 1) Framework checklist signed-off. 2) All apps meet baseline (logging, config, error standard). 3) Secrets in Key Vault. 4) Telemetry consistent. 5) Support runbooks available.
12 | Digital ID upgrade (100-point ID / myID) – design → prototype → plug into invite flow Stronger identity proofing for provider users (beyond ARN/DOB) | ASQA Portal (Next Gen) | RMA app (invitation + identity status) | Digital ID provider (myID/100-point), B2C custom policies, Web API, Dataverse, monitoring | Verified high-trust identity for portal access; future-ready compliance | Discovery: confirm requirement scope, user journeys, data fields, consent, error handling. Define integration approach (B2C policy + API). Build dummy/mimic in portal for demo path (as per KT). | Prototype integration in Dev/Test with limited scope. Define fallback (manual verification) + support model. | Hardening: security review, penetration-style negative tests, performance, monitoring, privacy. | Production-ready go-live plan + phased rollout (pilot group first) + BAU handover. | You + Jamie/Business + Security/Identity team + Platform | DoD: 1) Identity journey approved by business/security. 2) End-to-end integration works in PreProd. 3) Logs + audit + support model defined. 4) Pilot success criteria met. 5) Rollout plan for prod agreed.
9 | RMA Invite-only onboarding end-to-end (B2C → API → Dataverse → Dashboard) Provider user gets invite, verifies ARN/DOB, signs up, lands on right dashboard; no public sign-up allowed | ASQA Portal (Next Gen) (RMA portal pages) | RMA app (staff manage invitations, submissions, routing) | Azure AD B2C, Web API, Dataverse, App Insights, WAF, DNS/Gateway | Secure invite-only portal access working end-to-end; correct user-contact mapping; supportable errors | Stabilise invite flow in Dev/Test (invite email → ARN/DOB verify → signup). Implement no-bypass enforcement. Add reason codes + friendly error pages. Fix DevInt DNS/gateway so B2C→API reachable in DevInt. | Complete role routing (RTO/CEO/II) + verify across Test/PreProd. Confirm CAPTCHA requirement and implement if missing. Add regression pack (happy + negative paths). | Hardening: edge cases (duplicate contact, wrong ARN/DOB, expired invite, replay attack). Improve monitoring + alerts for auth failures and API issues. | Merge RMA work to main + execute full regression + production smoke. BAU handover pack ready. | You (RMA/B2C dev) + Jamie for priority/support; TechOps for gateway/WAF | DoD: 1) No public signup (invite required). 2) ARN/DOB validation enforced + logged. 3) Contact link created correctly. 4) Role routing works. 5) Friendly error pages + reason codes. 6) Dev/Test/PreProd/Prod smoke tests passed + monitoring alerts configured.